## Evidence
case | resource | slot | start | duration_days | available_capacity | unit | qualification | load_status | authority
CASE-017 | weld-booth and inspector capacity | SEA-BASE-017 | 2026-01-19 | 2 | 41 | HR | QUALIFIED | OPEN_AFTER_PROTECTED_LOAD | CURRENT
CASE-017 | weld-booth and inspector capacity | SEA-OT-017 | 2026-01-16 | 1 | 53 | HR | QUALIFIED | CONDITIONAL | SEPARATE_APPROVAL
CASE-017 | weld-booth and inspector capacity-A | SEA-A-017 | 2026-01-18 | 1 | 13 | HR | EXPIRED | OPEN | NOT_ELIGIBLE
CASE-017 | weld-booth and inspector capacity-B | SEA-B-017 | 2026-01-19 | 1 | 20 | HR | QUALIFIED | OUTAGE | NOT_AVAILABLE
CASE-017 | weld-booth and inspector capacity-C | SEA-C-017 | 2026-01-20 | 2 | 20 | HR | QUALIFIED | OPEN | CURRENT
CASE-018 | weld-booth and inspector capacity | SEA-OTHER-017 | 2026-01-19 | 1 | 41 | HR | QUALIFIED | RESERVED | OTHER_CASE
CASE-017 | weld-booth and inspector capacity-PDX | PDX-017 | 2026-01-19 | 2 | 41 | HR | QUALIFIED | OPEN | OUTSIDE_ORGANIZATION
CASE-017 | weld-booth and inspector capacity | SEA-ARCH-017 | 2026-01-08 | 1 | 41 | HR | QUALIFIED | ARCHIVED | SUPERSEDED