## Evidence
resource_or_control | window_ref | window_start | duration_days | candidate_capacity | unit | qualification | status | protected_load | economic_impact_usd | authority
downstream cure and assembly slots | wait_for_incumbent_recovery | 2026-01-21 | 1 | 47 | EA | QUALIFIED | OPEN | 4 | 0 | NORMAL
downstream cure and assembly slots / earlier-shift | EARLY-PROTECTED | 2026-01-19 | 1 | 23 | EA | QUALIFIED | PROTECTED_LOAD | 4 | 0 | NOT_DISPLACEABLE
downstream cure and assembly slots / alternate-A | ALT-A | 2026-01-20 | 1 | 15 | EA | QUALIFICATION_EXPIRED | OPEN | 0 | 0 | NOT_ELIGIBLE
downstream cure and assembly slots / alternate-B | ALT-B | 2026-01-21 | 1 | 23 | EA | QUALIFIED | MAINTENANCE_OUTAGE | 0 | 0 | NOT_ELIGIBLE
downstream cure and assembly slots / PDX | OTHER-PLANT | 2026-01-21 | 2 | 47 | EA | QUALIFIED | OPEN | 0 | 0 | OUTSIDE_CASE_SCOPE
downstream cure and assembly slots | ESCALATION-RAW | 2026-01-17 | 1 | 60 | EA | CONDITIONAL | UNAPPROVED | 0 | 1658 | SEPARATE_APPROVAL_REQUIRED
downstream cure and assembly slots / nearby-case | DISTRACTOR | 2026-01-21 | 1 | 47 | EA | QUALIFIED | RESERVED | 47 | 0 | OWNED_BY_CASE-019