## Evidence
risk_id | case | risk | likelihood | impact | owner | mitigation | status
R-052-A | CASE-052 | incorrect record selection | low | high | quality_engineer | cross-check immutable identifiers | OPEN
R-052-B | CASE-052 | unapproved scope expansion | medium | high | U-APPROVER | limit write to approved fields | MITIGATED