## Evidence
risk_id | case | risk | likelihood | impact | owner | mitigation | status
R-013-A | CASE-013 | incorrect record selection | low | high | shop_floor_controller | cross-check immutable identifiers | OPEN
R-013-B | CASE-013 | unapproved scope expansion | medium | high | U-APPROVER | limit write to approved fields | MITIGATED