## Evidence
case | resource | slot | start | duration_days | available_capacity | unit | qualification | load_status | authority
CASE-016 | finite load on each qualified assembly cell | SEA-BASE-016 | 2026-01-19 | 1 | 35 | HR | QUALIFIED | OPEN_AFTER_PROTECTED_LOAD | CURRENT
CASE-016 | finite load on each qualified assembly cell | SEA-OT-016 | 2026-01-15 | 1 | 46 | HR | QUALIFIED | CONDITIONAL | SEPARATE_APPROVAL
CASE-016 | finite load on each qualified assembly cell-A | SEA-A-016 | 2026-01-18 | 1 | 11 | HR | EXPIRED | OPEN | NOT_ELIGIBLE
CASE-016 | finite load on each qualified assembly cell-B | SEA-B-016 | 2026-01-19 | 1 | 17 | HR | QUALIFIED | OUTAGE | NOT_AVAILABLE
CASE-016 | finite load on each qualified assembly cell-C | SEA-C-016 | 2026-01-20 | 2 | 17 | HR | QUALIFIED | OPEN | CURRENT
CASE-017 | finite load on each qualified assembly cell | SEA-OTHER-016 | 2026-01-19 | 1 | 35 | HR | QUALIFIED | RESERVED | OTHER_CASE
CASE-016 | finite load on each qualified assembly cell-PDX | PDX-016 | 2026-01-19 | 2 | 35 | HR | QUALIFIED | OPEN | OUTSIDE_ORGANIZATION
CASE-016 | finite load on each qualified assembly cell | SEA-ARCH-016 | 2026-01-08 | 1 | 35 | HR | QUALIFIED | ARCHIVED | SUPERSEDED