## Evidence
case | resource | slot | start | duration_days | available_capacity | unit | qualification | load_status | authority
CASE-065 | service dispatch window | SEA-BASE-065 | 2026-01-16 | 2 | 92 | EA | QUALIFIED | OPEN_AFTER_PROTECTED_LOAD | CURRENT
CASE-065 | service dispatch window | SEA-OT-065 | 2026-01-14 | 1 | 99 | EA | QUALIFIED | CONDITIONAL | SEPARATE_APPROVAL
CASE-065 | service dispatch window-A | SEA-A-065 | 2026-01-15 | 1 | 30 | EA | EXPIRED | OPEN | NOT_ELIGIBLE
CASE-065 | service dispatch window-B | SEA-B-065 | 2026-01-16 | 1 | 46 | EA | QUALIFIED | OUTAGE | NOT_AVAILABLE
CASE-065 | service dispatch window-C | SEA-C-065 | 2026-01-17 | 2 | 46 | EA | QUALIFIED | OPEN | CURRENT
CASE-066 | service dispatch window | SEA-OTHER-065 | 2026-01-16 | 1 | 92 | EA | QUALIFIED | RESERVED | OTHER_CASE
CASE-065 | service dispatch window-PDX | PDX-065 | 2026-01-16 | 2 | 92 | EA | QUALIFIED | OPEN | OUTSIDE_ORGANIZATION
CASE-065 | service dispatch window | SEA-ARCH-065 | 2026-01-08 | 1 | 92 | EA | QUALIFIED | ARCHIVED | SUPERSEDED