## Evidence
risk_id | case | risk | likelihood | impact | owner | mitigation | status
R-003-A | CASE-003 | incorrect record selection | low | high | order_fulfillment_manager | cross-check immutable identifiers | OPEN
R-003-B | CASE-003 | unapproved scope expansion | medium | high | U-APPROVER | limit write to approved fields | MITIGATED